## Read_Me
PROJECT & TASK MANAGEMENT TRACKER
PROJECT OVERVIEW
This project was created in Google Sheets to organize tasks, monitor deadlines, and track progress across multiple projects.
BUSINESS PURPOSE
The goal is to help a project coordinator or manager quickly identify completed work, tasks in progress, upcoming deadlines, and overdue tasks.
TOOLS USED
• Google Sheets
• IF and COUNTIF formulas
• COUNTA formula
• Conditional formatting
• Dashboard charts and KPI metrics
KEY FEATURES
• Tracks 15 sample tasks across three projects.
• Records task owners, priorities, start dates, due dates, and statuses.
• Calculates days remaining until a deadline.
• Flags tasks as Complete, Overdue, Due Today, or On Track.
• Displays total tasks, completed tasks, in-progress tasks, overdue tasks, and completion rate.
• Visualizes task status using a chart.
SKILLS DEMONSTRATED
Data organization, spreadsheet formulas, deadline tracking, KPI reporting, conditional formatting, and dashboard design.
DATA DISCLAIMER
This is a practice portfolio project using fictional sample data. It was created to demonstrate spreadsheet and reporting skills.

## Task_Tracker
Task_ID | Project_Name | Task | Assigned_To | Priority | Start_Date | Due_Date | Status | Days_Remaining | Task_ Alert
T001 | Website Launch | Finalize project brief | Alex | High | 2026-10-19 | 2026-10-23 | Complete |  | Complete
T002 | Website Launch | Approve homepage design | Jordan | High | 2026-10-20 | 2026-10-24 | In Progress | -4 | Overdue
T003 | Website Launch | Write website copy | Taylor | Medium | 2026-10-20 | 2026-10-28 | In Progress | 0 | Due Today
T004 | Website Launch | Review mobile layout | Morgan | Medium | 2026-10-21 | 2026-10-26 | Not Started | -2 | Overdue
T005 | Website Launch | Test website links | Alex | Low | 2026-10-22 | 2026-10-29 | Not Started | 1 | On Track
T006 | Training Program | Prepare training materials | Jordan | High | 2026-10-19 | 2026-10-22 | Complete |  | Complete
T007 | Training Program | Schedule training sessions | Taylor | High | 2026-10-20 | 2026-10-23 | In Progress | -5 | Overdue
T008 | Training Program | Confirm attendee list | Morgan | Medium | 2026-10-20 | 2026-10-22 | Not Started | -6 | Overdue
T009 | Training Program | Send reminder emails | Alex | Low | 2026-10-21 | 2026-10-27 | Not Started | -1 | Overdue
T010 | Training Program | Collect feedback forms | Taylor | Medium | 2026-10-22 | 2026-10-30 | Not Started | 2 | On Track
T011 | Client Event | Confirm venue booking | Morgan | High | 2026-10-19 | 2026-10-21 | In Progress | -7 | Overdue
T012 | Client Event | Finalize catering order | Alex | High | 2026-10-20 | 2026-10-22 | Not Started | -6 | Overdue
T013 | Client Event | Prepare event schedule | Jordan | Medium | 2026-10-21 | 2026-10-25 | Not Started | -3 | Overdue
T014 | Client Event | Confirm guest attendance | Taylor | Medium | 2026-10-20 | 2026-10-24 | Complete |  | Complete
T015 | Client Event | Send post-event survey | Morgan | Low | 2026-10-22 | 2026-10-31 | Not Started | 3 | On Track
Formulas:
Days_Remaining = IF([Status]="Complete","",[Due_Date]-TODAY())
Task_ Alert = IF([Status]="Complete","Complete",IF([Due_Date]<TODAY(),"Overdue",IF([Due_Date]=TODAY(),"Due Today","On Track")))

## Dashboard
Project & Task Management Dashboard
Total Tasks | 15 | Task Status | Number of Tasks
Completed Tasks | 3 | Complete | 3
In Progress Tasks | 4 | In Progress | 4
Overdue Tasks | 8 | Not Started | 8
Completion Rate | 20%